## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project planning & reading assignment | 1 | 24/09/2025 | Read design, API docs, and planned implementation and components.
Project scaffold & environment setup | 1 | 24/09/2026 | Initialized Vite + Vue 3, installed Pinia, Router, Axios, created README.
API service & auth handling | 1 | 24/09/2027 | Implemented axios client, baseURL from .env and x-api-key header support.
Houses list (overview) & search | 2 | 24/09/2028 | Implemented listing grid, search input, clear behaviour, result count and paging.
Sorting & result handling | 1 | 25/09/2029 | Added sorting options (price, size) and handled empty / error states.
House detail page | 2 | 25/09/2030 | Detail display including all required fields and conditional edit/delete for owner.
Create listing form & validation | 2 | 25/09/2031 | Implemented create form, validation messages, API create and redirect to detail.
Edit listing | 2 | 25/09/2032 | Prefill form for editing, implement update API call and validation.
Delete listing & confirmation | 1 | 25/09/2033 | Delete flow with confirmation and cleanup of local 'my listings' store.
State management (Pinia) & localStorage | 2 | 26/09/2034 | Favorites and user's created listing ids stored in localStorage.
Favorites feature (bonus) | 1 | 26/09/2035 | Implemented favorite toggling and Favorites page.
About page (bonus) | 1 | 26/09/2036 | Added About page describing app and technologies.
Styling & responsiveness | 1 | 26/09/2037 | Applied styleguide colours, responsive grid and header; ensured mobile usability.
Testing, debugging & adjustments | 2 | 26/09/2038 | Manual testing, fixed edge-cases, improved UX and error handling.
Packaging & documentation | 1 | 26/09/2039 | Prepared README and zipped project for submission.
Total amount of hours | 30